## Sheet1
Kitchen Story Angular Agile Project Plan
Task Name | Priority | Owner | Start Date | End Date | Status
Sprint #1: Analysis and Design
Making Sprint Plan | High | Pravallika | 2022-08-25 | 2022-08-28 | Done
Specification document | Low | Pravallika | 2022-08-25 | 2022-08-28 | Done
Prepare Algorithm | High | Pravallika | 2022-08-25 | 2022-08-28 | Done
Create Flow Chart | Medium | Pravallika | 2022-08-25 | 2022-08-28 | Done
Setup Git Repository | High | Pravallika | 2022-08-25 | 2022-08-28 | Done
Sprint #2: Develop and Execute
Setup Environment | Medium | Pravallika | 2022-08-28 | 2022-08-01 | Done
Code css | High | Pravallika | 2022-08-28 | 2022-08-01 | Done
Code typescript | High | Pravallika | 2022-08-28 | 2022-08-01 | Done
Code for html | High | Pravallika | 2022-08-28 | 2022-08-01 | Done
Code to Navigate and close Application | Medium | Pravallika | 2022-08-28 | 2022-08-01 | Done
Sprint #3: Test, Fix & Install
Test the Application | High | Pravallika | 2022-08-01 | 2022-08-05 | Done
Fix issues | High | Pravallika | 2022-08-01 | 2022-08-05 | Done
Regression Test | Low | Pravallika | 2022-08-01 | 2022-08-05 | Done
Upload to Git Repository | Medium | Pravallika | 2022-08-01 | 2022-08-05 | Done
Submit Project | High | Pravallika | 2022-08-05 | 2022-08-05 | Done